## Sheet1
Team 04: Codevengers Project: Job Search and Networking
Task Name | Start Date | End Date | Duration | Roles | Assigned | Depended | Progress | Review and Approval
PROJECT PLANNING AND FINALIZATION | 2023-12-29 16:00 | 2024-01-01 18:00 | 3 days | AMNA SHAIKH | PM | NONE | COMPLETED
SOFTWARE REQUIREMENTS SPECIFICATIONS (SRS) | 2023-12-29 16:00 | 2024-01-01 18:00 | 3 days | AHSAN ALI | BA | NONE | COMPLETED
UI/UX | 2024-01-02 08:30 | 2024-01-06 08:30 | 4 days | SAQIB JAMIL | UI/UX | BA | TO BE DONE
SIGN UP & LOGIN | 2024-01-06 10:00 | 2024-01-12 13:00 | 6 days | SAMI & MUQEET | Dev | BA/UI/UX | TO BE DONE
HOME PAGE & DASHBOARD | 2024-01-06 10:00 | 2024-01-12 13:00 | 6 days | UZAIR & SAMI | Dev | BA/UI/UX | TO BE DONE
CREATE JOB & APPLY FOR JOB | 2024-01-06 10:00 | 2024-01-13 13:00 | 7 days | MUQEET & UZAIR | Dev | BA/UI/UX | TO BE DONE
DATABASES (schemas etc) | 2024-01-13 10:00 | 2024-01-21 17:00 | 8 days | HASIN & YASEEN | Dev | BA/UI/UX/DEV | TO BE DONE
APIs | 2023-01-13 10:00 | 2024-01-21 17:00 | 8 days | FURQAN & HASIN | Dev | BA/UI/UX/DEV | TO BE DONE
INTEGRATION | 2024-01-13 10:00 | 2024-01-21 17:00 | 8 days | YASEEN & FURQAN | Dev | BA/UI/UX/DEV | TO BE DONE
TESTING AND QUALITY ASSURANCE | 2024-01-21 18:30 | 2024-01-24 15:30 | 4 days | KHUZAIMA UMAIR | TESTER | Dev/BA | TO BE DONE
PROJECT SUBMISSION AND VIVA | 2024-01-25 16:00 | 2024-01-25 20:00 | 1 days | ALL | ALL | ALL | TO BE DONE